Project Planning Phase

Project Planning Template (Product Backlog, Sprint Planning, Stories, Story points)

| Date | 30 September 2026 |
| --- | --- |
| Team ID | SWTID-2026-7743 |
| Project Name | AI FAQ Assistant API |
| Maximum Marks | 5 Marks |

Product Backlog, Sprint Schedule, and Estimation (4 Marks)

Use the below template to create product backlog and sprint schedule

| Sprint | Functional Requirement (Epic) | User Story Number | User Story / Task | Story Points | Priority | Team Members |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | Project Setup & Authentication | USN-1 | As a developer, I can set up the FastAPI project with Docker and a common repository structure. | 2 | High |  |
| Sprint-1 |  | USN-2 | As an administrator, I can register my organisation with email and password and receive an API key. | 3 | High |  |
| Sprint-1 |  | USN-3 | As an administrator, I can log in to the dashboard using email and password. | 3 | High |  |
| Sprint-1 | FAQ Ingestion | USN-4 | As an administrator, I can upload FAQs as CSV or JSON files. | 5 | High |  |
| Sprint-1 |  | USN-5 | As an administrator, I can upload PDF documents whose text is extracted and split into chunks. | 5 | Medium |  |
| Sprint-1 |  | USN-6 | As the system, I convert FAQ chunks into embeddings and store them in the vector database. | 2 | High |  |
| Sprint-2 | Question Answering | USN-7 | As a user, I can send a question to POST /v1/ask and receive an answer. | 5 | High |  |
| Sprint-2 |  | USN-8 | As a user, I receive answers generated only from the most relevant FAQ content. | 5 | High |  |
| Sprint-2 | Answer Reliability | USN-9 | As a user, I can see the source FAQ for every answer. | 3 | High |  |
| Sprint-2 |  | USN-10 | As a user, I get an "I don't know / contact support" reply when confidence is low. | 3 | High |  |
| Sprint-2 | Performance & Validation | USN-11 | As a developer, repeated questions are served from the Redis cache. | 2 | Medium |  |
| Sprint-2 |  | USN-12 | As a developer, invalid or empty requests return clear error messages. | 2 | Medium |  |
| Sprint-3 | FAQ Management | USN-13 | As an administrator, I can view, edit and delete FAQs. | 5 | High |  |
| Sprint-3 | Feedback & Analytics | USN-14 | As a user, I can give thumbs up / down feedback on an answer. | 2 | Medium |  |
| Sprint-3 |  | USN-15 | As an administrator, I can see top questions and unanswered questions. | 5 | Medium |  |
| Sprint-3 | API Access Control | USN-16 | As an administrator, I can revoke keys and the API applies rate limiting per key. | 3 | High |  |
| Sprint-3 | Multilingual Support | USN-17 | As a user, I can ask in Tamil or Hindi and get the answer in the same language. | 5 | Medium |  |
| Sprint-4 | Integration | USN-18 | As a business, I can embed a chat widget on my website with a few lines of code. | 5 | Medium |  |
| Sprint-4 | Documentation | USN-19 | As a developer, I can read complete API documentation (Swagger UI and README). | 2 | Medium |  |
| Sprint-4 | Testing & Quality | USN-20 | As a team, we run unit, integration and load tests on the API. | 5 | High |  |
| Sprint-4 |  | USN-21 | As a team, we complete user acceptance testing and fix reported bugs. | 3 | High |  |
| Sprint-4 | Deployment | USN-22 | As a team, we deploy the application to the cloud with a CI/CD pipeline. | 5 | High |  |

Project Tracker, Velocity & Burndown Chart: (4 Marks)

| Sprint | Total Story Points | Duration | Sprint Start Date | Sprint End Date (Planned) | Story Points Completed (as on Planned End Date) | Sprint Release Date (Actual) |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | 20 | 6 Days | 05 Oct 2026 | 10 Oct 2026 |  |  |
| Sprint-2 | 20 | 6 Days | 12 Oct 2026 | 17 Oct 2026 |  |  |
| Sprint-3 | 20 | 6 Days | 19 Oct 2026 | 24 Oct 2026 |  |  |
| Sprint-4 | 20 | 6 Days | 26 Oct 2026 | 31 Oct 2026 |  |  |

Velocity:

Our sprint duration is 6 days and the team velocity is 20 story points per sprint (80 story points across 4 sprints). Average velocity (AV) per iteration unit = velocity ÷ sprint duration = 20 ÷ 6 = 3.33 story points per day.

Burndown Chart:

A burn down chart is a graphical representation of work left to do versus time. It is often used in agile software development methodologies such as Scrum. However, burn down charts can be applied to any project containing measurable progress over time.

Planned burndown for the AI FAQ Assistant API (80 story points over 4 sprints). Actual progress will be added to the chart after each sprint.

https://www.visual-paradigm.com/scrum/scrum-burndown-chart/

https://www.atlassian.com/agile/tutorials/burndown-charts

Reference:

https://www.atlassian.com/agile/project-management

https://www.atlassian.com/agile/tutorials/how-to-do-scrum-with-jira-software

https://www.atlassian.com/agile/tutorials/epics

https://www.atlassian.com/agile/tutorials/sprints

https://www.atlassian.com/agile/project-management/estimation

https://www.atlassian.com/agile/tutorials/burndown-charts